## Introduction
Tool 2 template: Lessons learned tracking sheet
Introduction
Developing a better practice financial statements process is an iterative process. It is important to take time at the end of each cycle to consider what went well and what could be improved. This tracking sheet helps finance teams to communicate the issues and challenges from the previous financial statement process and document the proposed solutions for implementation. Lessons learned in progress A tracking sheet, such as this one, allows the team to record what didn't go to plan and track the progress of improvements. Completed lessons learned This register is for keeping track of completed items from previous year's lessons. It is important to keep a record of past items as a reference as this assists in the preparation of position papers and supporting information for future decisions. Positive lessons It is helpful to keep track of the positive lessons in addition to negative lessons.

## Lessons learned in progress
Financial statements
Lessons learned in progress tracking sheet
Ref | Key topic | Identified issue | Proposed resolution | Action assigned to | Progress to audit committee | Internal only | Status | Planned completion | Actual completion | Feedback/comments
Lessons learned identified in 202x - 202x financial year
1 | Financial statements model | The Model didn't detect several internal consistency errors that the auditors picked up. | Review internal consistency functionality and ensure it is working | Financial statements | No | Yes | In progress | 2021-06-30 |  |  | 1
2 | Valuation of Land and Buildings | Valuation report wasn't available untill just before sign-off which resulted in a late lodgement of financial statements | Review planning for next reporting cycle and ensure valuation reports are obtained in a timely manner | Financial statements | Yes | No | Not started | 2021-06-30 |  |  | 1
3 | [10 empty] | 1
4 | [10 empty] | 1
5 | [10 empty] | 1
6 | [10 empty] | 1
Lessons Learned identified in 2014 - 2015 Financial Year
1 | [10 empty] | 1
2
3
4
5
Lessons learned to continue on a regular basis
1 | [10 empty] | 1
2 | [10 empty] | 1
3 | [10 empty] | 1
4 | [10 empty] | 1
5 | [10 empty] | 1

## Completed lessons learned
Financial statements
Completed lessons learned tracking sheet
Ref | Key topic | Identified issue | Proposed resolution | Action assigned to | Progress to audit committee | Internal only | Status | Planned completion | Actual completion | Feedback/comments
Lessons learned identified in 202x - 202x financial year - COMPLETED
1 | Use of external consultants for corporate services and financial statement preparation | The external consultant timetable for financial statement preparation did not align with external audit expectations and timetable which resulted in delays in completing the audit and signing off the financial statements. | Ensure the external consultant attends external audit meetings such as pre-planning and audit entrance meeetings to ensure concurrence of financial statement preparation timetable. | Financial statements | Yes | No | Completed | 2021-11-28 | 2021-12-08 | CFO with the external consultant to discuss timing issue and arranged for them to attend key meetings with external auditors to discuss and agree the timetable for financial statement preparation. | 1
2 | SIMS reporting | SIMS was not updated for late adjustments to the financial statements. | Finance manager regularly advises the responsible officer of changes and adjustments to financial statements, to facilitate the timely update of SIMS. | Financial statements | No | Yes | Completed | 2021-10-31 | 2021-11-15 | Finance manager met with responsible officer to discuss timely updates to SIMS and organise for weekly meetings to advise of changes and adjustments to financial statements. | 1
3 | [10 empty] | 1
4 | [10 empty] | 1
5 | [10 empty] | 1
6 | [10 empty] | 1
7 | [10 empty] | 1
8 | [10 empty] | 1
9 | [10 empty] | 1
10 | [10 empty] | 1
11 | [10 empty] | 1
12 | [10 empty] | 1
13 | [10 empty] | 1
14 | [10 empty] | 1
15 | [10 empty] | 1
16 | [10 empty] | 1
17 | [10 empty] | 1
18 | [10 empty] | 1
19 | [10 empty] | 1

## Positive lessons
202x-2x Financial statements
Positive lessons
Ref | Key topic | Identified issue
1 | Project plan | Project Plan allowed easy tracking for management on the progress of the financial statements and allowed them to reallocated resources where pressures where building.
2 | Adoption of new accounting standards | Preparation of accounting position papers that clearly outlined the new requirements, our assessment and impact assisted greatly in providing the necessary assurance to the audit committee and obtaining their approval.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17

## Metadata (hidden)
Raw data
Section | Yes/No | Status
Accounts payable team | Yes | Not started
Accounts receivable team | No | In progress
External budgets |  | Issues
Financial statements |  | Completed
All |  | Overdue