## Introduction
Tool 6 example: Financial statements project plan
Introduction
A detailed project plan outlines the activities to be completed in the preparation process, including the timeline and responsibilities for the completion of each activity and its status. This example project plan assumes a year-end date of 30 June 202x. It is better practice that the day of the week and the date be shown in the ‘due date’ column. The example project plan should be tailored to meet the entity’s particular circumstances and needs. The plan does not necessarily cover all possible events and actions. Some smaller entities could have a shorter elapsed time if their tasks are less complex.

## June year end 202x-2x timetable
| Manual tracking | Completed |  |  |  | Overdue
|  | WIP |  |  |  | Due for completion
| 202x-2x Financial statements project plan | NA
Phase | Task name | Start | Finish | 43502 | Overdue | Status | Comments | Primary resource | Secondary resource | Submitted for review | First review | Edits processed | Manager review | Edits processed2 | Cleared | Additional comments
1. | End of period Activities | 0 | 0
Update financial statements template
Review lessons learned
Audit confirmation letters
2. | Systems Processing | 0 | 0
Invoices to be processed in FMIS
Last payment run for June
EOM payroll accrual files for June 202x
Close travel module and goods receipt module in FMIS
Final credit card export for the month
Close accounts payable
Close accounts receivable
Final bank statement processing
Close June 202x period in FMIS
Open July 202x and period 13 in FMIS
3. | Period 13 activities | 0 | 0
Asset revaluation
4. | Employee leave liabilities | 0 | 0
Leave liability reconciliations
5. | SIMS reporting | 0 | 2020-07-13
Late adjustments reported to Treasury
| Deadline to submit to Treasury |  | 2020-07-13 | 523
6 | Financial statements | 0 | 0
Draft primary financial statements (week 1)
Statement of comprehensive income
Statement of financial position
Statement of changes in equity
Statement of cash flows
Rate setting statement
1. Financial performance
| 1.1: Expenses | 0 | 0
1.1A: Employee benefits
1.1B: Supplier expenses (goods and services)
1.1B: Other supplier expenses
1.1C: Grants and subsidies
1.1D: Finance costs
1.1E: Write-down and impairment of assets
1.1F: Other expenses
1.1G: Depreciation and amortisation
| 1.2: Revenue and gains | 0 | 0
1.2A: Rates or User charges and fees
1.2B: Grants revenue
1.2C: Other revenue
1.2D: Gains from sales of assets
1.2E: Other gains
1.2F: Income from State Government
| 1.3: Other comprehensive income | 0 | 0
1.3: Other comprehensive income
2. Financial position
| 2.1: Financial assets | 0 | 0
2.1A: Cash and cash equivalents
2.1B: Trade and other receivables
2.1C: Other financial assets
2.2: Non-financial assets
2.2A: Reconciliation of the opening and closing balances of property, plant and equipment and intangibles
2.2B: Other non-financial assets
2.3: Payables
2.3A: Creditors
2.3B: Other payables
2.3B: Unearned income
2.4: Other provisions
2.4: Other provisions
3. Employee related items
3.1: Employee provisions and disclosures
3.1A: Employee provisions
3.2B: Key management personnel remuneration
3.3C: Related party disclosures
4. Risks and contingencies
4.1: Contingent assets and liabilities
4.1A: Contingent assets and liabilities
4.2: Financial instruments
4.2A: Catorgories of financial instruments
4.2B: Fair value of financial instruments
4.2C: Credit risk
4.2D: Liquidity risk
4.2E: Market risk
5. Other disclosures
5.1: Major land transactions
5.1: Details including current year transactions, expected future cash flows and assets and liabilities
5.2: Explanations of major variances
5.2A: Budgetary reports
5.2B: Major budget variances
7. | CFO file note | 0 | 0 | -43502 | Overdue
Controlled CFO file note
CFO sign-off
8 | Annual reporting to Treasury | 0 | 0 | -43502 | Overdue
Annual reporting to Treasury (SIMS)
CFO sign-off
Deadline to submit annual reporting (actuals) to Treasury
9. | Independent review | 0 | 0 | -43502 | Overdue
Review of financial statements by independent contractor
10. | CFO review | 0 | 0 | -43502 | Overdue
Review of financial statements by CFO
11. | OAG audit | 0 | 0 | -43502 | Overdue
OAG audit of Entity financial statements
12. | Audit committee |  | 0 | -43502 | Overdue
Audit Committee Meeting
13. | Annual report (State entity example) | 0 | 0 | -43502 | Overdue
Overview
Performance management framework
Agency performance
Signficant Issues Impacting the Agency
Disclosures and legal compliance
Final key performance indicators
Other statutory information
14. | Post year end activities | 0 | 0 | 0
Management representation letter
Accountable authority sign off
Review lessons learned
Formulas:
Completed = MIN([Completed, row below]:[Completed, row below])
Completed = MIN([Completed, row below]:C19)
Finish = MAX([Finish, row below]:[Finish, row below])
Finish = MAX([Finish, row below]:D19)